# CourseCraft — Estimation Sheet

Case Study 108 | Version 1.0 | 1 October 2026

Purpose: Walk through the production and revenue arithmetic using only the figures in the case, and explain what the results do—and do not—tell us.

## 1. Inputs supplied by the case

| Input | Value | Unit / meaning |
| --- | --- | --- |
| Recorded content per course | 12 | content-hours |
| Recording and editing effort rate | 3 | work-hours per content-hour |
| Editors | 2 | people |
| Availability per editor | 30 | work-hours per week |
| Revenue per enrolment | ₹4,500 | gross planning revenue per enrolment |
| Target enrolments | 150 | enrolments per course in year one |
| Faculty recording capacity | 8 | courses within the next 3 months |
| Platform readiness | 10 | weeks (separate from content production) |

These calculations use only the case figures. No extra enrolments, production capacity, or contingency has been assumed.

## 2. Formulae

Production effort per course = content-hours per course × work-hours per content-hour.

Production effort for N courses = effort per course × N.

Weekly editor capacity = number of editors × hours/editor/week.

Editor-capacity duration = total production effort ÷ weekly editor capacity.

Year-one gross revenue scenario = courses × target enrolments/course × revenue/enrolment.

## 3. Step-by-step production effort

### Per course

12 content-hours/course × 3 work-hours/content-hour = 36 work-hours/course

Estimated production effort: 36 work-hours per course. This includes the combined recording-and-editing rate as specified in the brief; it is not 36 hours of editing alone.

### 8-course cohort

36 work-hours/course × 8 courses = 288 work-hours

Estimated total: 288 work-hours.

### 30-course target

36 work-hours/course × 30 courses = 1,080 work-hours

Estimated total: 1,080 work-hours.

## 4. Step-by-step editor-capacity duration

### Weekly available capacity

2 editors × 30 hours/editor/week = 60 editor-hours/week

### 8 courses

288 work-hours ÷ 60 editor-hours/week = 4.8 weeks

Editor-capacity duration: 4.8 weeks at full stated editor utilisation, assuming inputs are ready, work can be allocated without interruption, and all stated production effort can be performed by the editor pool.

### 30 courses

1,080 work-hours ÷ 60 editor-hours/week = 18 weeks

Editor-capacity duration: 18 weeks under the same assumptions. This is an editor-capacity lower-bound style calculation once content is available; it does not solve the faculty recording bottleneck. The brief only supports 8 recordings in the next 3 months, so the remaining 22-course recording schedule is unknown.

## 5. Year-one revenue scenario

### Revenue per course at the stated target

₹4,500/enrolment × 150 enrolments/course = ₹675,000 per course

### 8 courses

₹675,000/course × 8 courses = ₹5,400,000

Scenario gross revenue for 8 courses: ₹5,400,000 (₹54 lakh).

### 30 courses

₹675,000/course × 30 courses = ₹20,250,000

Scenario gross revenue for 30 courses: ₹20,250,000 (₹2.025 crore).

These figures are gross scenario arithmetic only. They assume every course reaches the stated 150-enrolment target and every enrolment yields ₹4,500. They exclude refunds, discounts, taxes, payment charges, operating costs, timing, and other financial adjustments because none were specified. They are not a forecast or guarantee.

## 6. Consolidated estimate

| Scenario | Content effort | Weekly editor capacity | Editor-capacity duration | Revenue scenario |
| --- | --- | --- | --- | --- |
| 1 course | 36 work-hours | 60 editor-hours/week | 0.6 capacity-weeks (36 ÷ 60) | ₹675,000 at 150 enrolments |
| 8 courses | 288 work-hours | 60 editor-hours/week | 4.8 weeks | ₹5,400,000 |
| 30 courses | 1,080 work-hours | 60 editor-hours/week | 18 weeks | ₹20,250,000 |

For one course, 0.6 weeks is the editor-pool capacity equivalent—not a promise that a single course will be finished in that time.

## 7. Schedule interpretation and estimate limits

The 8-course editor calculation (4.8 capacity-weeks) does not mean the courses will be ready 4.8 weeks after project start. Faculty recording is outside the IT team’s control and can produce only 8 courses within the next 3 months. If all recordings are handed over only at the end of that window, editing then adds 4.8 weeks at full capacity, before any validation/rework. The Project Plan uses that conservative, clearly labeled handoff assumption and a one-week validation allowance for schedule modelling.

A full 30-course launch cannot be dated from supplied data: the editor pool needs 18 capacity-weeks once all course content is available, while faculty’s capacity beyond the first 8 courses is unspecified. The platform’s 10-week readiness date is not a content-readiness date.

## 8. Assumptions and confidence

| Estimate | Assumptions | Confidence |
| --- | --- | --- |
| 36 work-hours/course | 12 content-hours and 3 work-hours/content-hour apply uniformly to each course. | High arithmetic confidence; medium input applicability. Formula is direct, but course-to-course variation is unknown. |
| 288 hours / 4.8 capacity-weeks for 8 | Both editors are available for 30 productive hours/week; no leave, coordination loss, rework, or queue delay; work can be shared. | High arithmetic confidence; low-to-medium elapsed-date confidence. Faculty handoffs are uncertain. |
| 1,080 hours / 18 capacity-weeks for 30 | Same editor assumptions; all 30 content packages are available. | High arithmetic confidence; low schedule confidence. Faculty capacity and delivery dates for 22 additional courses are unknown. |
| Revenue scenarios | ₹4,500 and 150 enrolments/course apply to every course in year one. | High arithmetic confidence; low forecast confidence. Actual enrolment and net revenue are not supplied. |

## 9. Why an estimate is not a promise

These numbers are estimates because they depend on the supplied inputs and on how the work is actually delivered. Faculty availability, the timing and quality of recordings, editor workload, rework, reviews, integrations, and approvals can all change the calendar date. The revenue figures are target-based scenarios, not forecasts. Refresh the estimate when course handoff dates, actual effort, launch scope, and enrolment results are known.