# CourseCraft — Project Plan

Case Study 108 | Version 1.0 | 1 October 2026

Planning baseline: This plan models a first launch with up to 8 content-ready courses, subject to the Director’s approval. The platform should support a 30-course catalogue, but the brief confirms recordings for only 8 courses in the next 3 months.

## 1. Executive schedule decision

The platform is expected to be ready in 10 weeks, but that does not mean the courses are ready to teach. In the 30-course scenario, the supplied production effort converts to 18 editor-capacity weeks—an 8-week gap beyond the software plan. For an 8-course phase, the production estimate is 4.8 capacity-weeks once the recordings are available. Faculty can record only 8 courses in the next 3 months, so the actual first-launch date depends on when accepted recordings arrive.

The detailed network below is a planning scenario, not a promised date. It assumes the 8-course recording batch arrives at the end of a 12-week window, then allows 4.8 capacity-weeks for production and one assumed week for validation. Batch handoffs could overlap production and finish sooner; late recordings or rework could make it later. The Director should confirm whether to launch a ready subset or wait for more courses.

## 2. Scope and planning assumptions

### Supplied case data

Platform readiness: 10 weeks.

Faculty can record 8 courses in the next 3 months.

Per course: 12 recorded content hours; recording and editing take 3 work hours per content hour.

Two editors, each available 30 hours/week.

Launch ambition: 30 courses; no assumption that the ambition is achievable with current content capacity.

### Explicit planning assumptions (to validate)

“Next 3 months” is represented as a 12-week planning window. This is a calendar approximation for scheduling only.

A conservative handoff model assumes the batch of 8 recordings is available at the end of week 12, followed by a 4.8-week production-capacity block and content validation. No batch dates were supplied. Since the stated effort rate combines recording and editing, validate the activity split before treating this as an editorial-only forecast; actual batch handoffs may overlap work.

The 10-week platform duration is represented by a 2+2+4+2 week work breakdown; component durations are planning allocations that sum to the supplied 10 weeks, not separately supplied estimates.

Content validation/release preparation is one week for schedule modelling only; it is not supplied project data.

Activities start at week 0 and durations use elapsed weeks; resource levelling and holidays are not modelled. Platform staffing numbers are unknown and are not invented.

A staged cohort of up to 8 is used as a schedule scenario, subject to Director approval. A 30-course fully recorded launch requires a revised plan and faculty commitment.

## 3. WBS (work breakdown structure)

| WBS | Work package | Output / exit criterion |
| --- | --- | --- |
| 1.0 | Initiation and governance | Approved scope decision, roles, change control, stakeholder workshop. |
| 1.1 | Requirements and analysis | Baselined SRS, certificate policy decisions, NFR targets approved. |
| 1.2 | Architecture and design | UML package, interfaces for payment/video, security design. |
| 1.3 | Platform implementation | Catalogue, enrolment/payment, playback/progress, quizzes/certificates, dashboards. |
| 1.4 | Integration and platform QA | Integrated build, security/access tests, load and functional evidence. |
| 1.5 | Faculty content readiness | Recording plan, 8 course recordings supplied, editor handoffs tracked. |
| 1.6 | Production-capacity block and packaging | Production effort allocated for the content-backed cohort under the case-rate proxy; actual recording/editing split to be validated. |
| 1.7 | Content validation | Playback, metadata, captions/accessibility checks as approved; assets marked ready. |
| 1.8 | Release readiness | Course catalogue/content reconciliation, support readiness, go/no-go. |
| 1.9 | Launch and closure | Production release, initial monitoring, lessons learned and handover. |

## 4. Network logic and forward/backward pass

The two workstreams start together: the platform path is A → B → C → D, while content follows E → F → G. Both must be ready before the launch checkpoint I. “Float” is the time a non-critical task can slip before it delays the modeled week-17.8 launch.

| ID | Activity | Duration (weeks) | Predecessor | ES | EF | LS | LF | Total float | Critical? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Requirements/workshop and baseline | 2.0 | — | 0.0 | 2.0 | 7.8 | 9.8 | 7.8 | No |
| B | Architecture, UX, and detailed design | 2.0 | A | 2.0 | 4.0 | 9.8 | 11.8 | 7.8 | No |
| C | Platform build (feature implementation) | 4.0 | B | 4.0 | 8.0 | 11.8 | 15.8 | 7.8 | No |
| D | Integration, platform QA, security/UAT fixes | 2.0 | C | 8.0 | 10.0 | 15.8 | 17.8 | 7.8 | No |
| H | Milestone: platform ready | 0.0 | D | 10.0 | 10.0 | 17.8 | 17.8 | 7.8 | No |
| E | Faculty record and hand off 8 courses | 12.0 | — | 0.0 | 12.0 | 0.0 | 12.0 | 0.0 | Yes |
| F | Production capacity / package 8-course batch | 4.8 | E | 12.0 | 16.8 | 12.0 | 16.8 | 0.0 | Yes |
| G | Content validation and release packaging | 1.0 | F | 16.8 | 17.8 | 16.8 | 17.8 | 0.0 | Yes |
| I | Milestone: content-backed launch/go-live | 0.0 | G and H | 17.8 | 17.8 | 17.8 | 17.8 | 0.0 | Yes |

Forward-pass formulas: EF = ES + duration; for activities with multiple predecessors, ES = maximum predecessor EF. Backward-pass formulas: LS = LF − duration; LF = minimum successor LS. Total float: TF = LS − ES (equivalently LF − EF).

Critical path: E → F → G → I (12 + 4.8 + 1 + 0 = 17.8 weeks). Platform path reaches readiness at week 10 and has 7.8 weeks of float in this baseline. The non-critical task floats are explicitly shown for A, B, C, D, and H. If platform tasks consume their float or content dates change, recalculate the path.

## 5. Gantt chart (weeks from project start)

Each █ is roughly one week. The diamonds mark zero-duration checkpoints—not extra work.

Week →  0    2    4    6    8    10   12   14   16  17.8
A Req.  ██████████
B Design      ██████████
C Build            ████████████████████
D QA/UAT                               ██████████
H Platform ready                                  ◆ (10.0)
E Record  ██████████████████████████████████████████████████████████
F Prod.                                                   ████████████████████████
G Validate                                                                  █████
I Launch                                                                         ◆ (17.8)

Milestones: requirements/design baseline at completion of A/B (week 4); platform ready (week 10); first 8-course content batch ready after validation (week 17.8 in the conservative model); content-backed launch (week 17.8). The milestone times are checkpoints, not durations.

## 6. Resource allocation

| Resource | Supplied availability / planned use | Constraint or action |
| --- | --- | --- |
| Editors | 2 × 30 hours/week = 60 editor-hours/week shared capacity. | Supplied production-rate arithmetic gives 288 work-hours for 8 courses (4.8 capacity-weeks) and 1,080 for 30 (18 capacity-weeks). Confirm how the combined recording/editing effort maps to editor work; track rework separately. |
| Faculty | Brief says 8 courses can be recorded in the next 3 months. | Individual faculty/course dates and hours are not supplied. Obtain named commitments and weekly handoff schedule; escalate any gap. |
| IT / engineering | Platform ready in 10 weeks. | Role counts and individual availability are not supplied. Assign owners for each WBS package before baseline. |
| Director / Centre admin | Decision-making, policy approval, course prioritisation and go/no-go. | Confirm staged launch, course selection, pricing, certificate policy, and operations owner. |

## 7. Launch options and decision gate

Option A — Staged release: launch a content-ready cohort of up to 8 courses when platform, content, security, and support checks pass. This best matches the stated near-term faculty capacity.

Option B — 30-course content-backed launch: hold launch until all 30 recordings are ready and edited. The editor-only minimum is 18 capacity-weeks once all recordings are ready; faculty capacity for the other 22 courses and timing are not given, so no defensible launch date can be promised.

Option C — Platform catalogue for 30, content staged: configure the platform for 30 courses while publishing only ready courses. This meets a 30-course technical/catalogue objective, not a 30-course learner-ready objective.

The Director should record which meaning of “30 at launch” is intended. Do not report an unrecorded course as launch-ready.

## 8. Monitoring and change control

At the weekly check-in, compare accepted recordings with the plan, editor hours with the 60-hour weekly capacity, and the platform milestones with their target dates. Review rework, open risks/issues, test readiness, and the current launch forecast. If scope, capacity, or a provider changes, recalculate the network and float before sharing a new date.