# CourseCraft — Risk Register & Closure Note

Case Study 108 | Version 1.0 | 1 October 2026

Status: Planning-stage risk baseline. No project issue was reported in the brief; the issue log is kept separate and currently has no confirmed entries.

## 1. Risk method

A risk is a problem that might happen; an issue is a problem that has already happened. We score each risk from 1 to 5 for probability and impact, then multiply the scores (P × I) to compare exposure. These ratings help the team prioritise discussion; they are planning judgements, not precise predictions.

| Score | Probability interpretation | Impact interpretation |
| --- | --- | --- |
| 1 | Rare | Negligible; little schedule/scope effect |
| 2 | Unlikely | Minor; recoverable within a work package |
| 3 | Possible | Moderate; rework or milestone pressure |
| 4 | Likely | Major; launch, security, or target impact |
| 5 | Almost certain / constraint already strongly indicated | Severe; launch objective cannot be met without a decision/change |

For this draft, exposures of 15–25 are High, 8–14 are Medium, and 1–7 are Low. These bands are proposed and should be confirmed by the project sponsor.

## 2. Main risks, ranked by exposure

| Rank | ID / risk event | P | I | Exposure | Response strategy and actions | Owner | Trigger / review point |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | R-01 Faculty recording delay: the brief supports 8 courses in 3 months, while the launch target is 30. Late handoffs could leave courses without ready content. | 5 | 5 | 25 High | Agree named handoff dates and define whether launch means 8 ready courses or 30. Track content separately from software; publish only accepted courses. If recordings slip, stage the launch or rebaseline. | Director (accountable); faculty leads (content); project manager (schedule) | No course commitments, a late handoff, or unresolved launch definition. Review weekly. |
| 2 | R-03 Launch-scope mismatch: the platform may be ready at week 10 while content for a 30-course launch is still in production. | 4 | 5 | 20 High | Decide in writing whether 30 means catalogue entries or fully ready courses. Track both readiness gates; stage the release or rebaseline if 30 ready courses are required. | Director (decision); project manager (control) | The meaning of “30 at launch” is unclear, or platform and content readiness diverge. Review at steering checkpoints. |
| 3 | R-02 Editor workload or rework: late or rejected recordings could exceed the editors’ shared 60 hours per week and delay publication. | 4 | 4 | 16 High | Book editor time, use agreed asset checklists, batch work where possible, and track effort/rework. If the queue grows, reprioritise or revise dates; extra capacity needs approval. | Content production lead / editor lead | Actual hours exceed plan, assets are repeatedly rejected, or the queue exceeds available editor time. Review weekly. |
| 4 | R-04 Payment integration failure: provider or callback errors could give a learner the wrong access status or require manual reconciliation. | 3 | 5 | 15 High | Test and verify callbacks; handle duplicates safely; reconcile provider references. If payment cannot be verified, pause access and use the approved reconciliation process. | IT integration lead | Provider decision is late, callback tests fail, or payment and enrolment records do not match. Review during integration. |
| 5 | R-05 Certificate rules are unclear: pass, retake, refund, or completion uncertainty could lead to inconsistent awards or learner disputes. | 3 | 5 | 15 High | Approve and version the 70% rule and exceptions; test boundary cases. Hold automatic certificate issue until policy is clear; send exceptions to authorised review. | Director / academic policy owner | The threshold or certificate rules are not approved before testing, or stakeholders disagree. Review before UAT. |
| 6 | R-06 Video service trouble: an outage, slow playback, or weak access protection could disrupt lessons or expose content. | 3 | 4 | 12 Medium | Test availability and access controls; monitor the pilot. If lessons fail, pause the affected course content and follow the approved learner communication plan. | IT service owner | Playback misses its target, errors repeat, or an access-control issue is found. Review during the pilot. |
| 7 | R-07 Security or privacy gap: a late policy/control issue could delay release or expose learner or payment information. | 2 | 5 | 10 Medium | Confirm policy and data ownership early; limit data collection; secure access and connections; test recovery. Block launch for unresolved critical findings. | IT/security owner | Policy remains unknown, a critical/high scan finding appears, or an access test fails. Review at each release gate. |
| 8 | R-08 Revenue scenario mistaken for a promise: gross targets may be presented as actual or guaranteed income. | 3 | 3 | 9 Medium | Label the figures as target-based scenarios. Track actual enrolments and costs separately, update projections with observed data, and avoid spending against unverified revenue. | Director / finance owner | A scenario is reported as committed revenue, or enrolments differ from target. Review monthly after launch. |

### 2.1 Risk review cadence

Review high-exposure risks each week and at the scope, content, integration, UAT, and go/no-go checkpoints. If a risk happens, open an issue with an owner and next action. Keep the risk entry too if there is still a chance of further impact.

## 3. Probability-impact matrix

Cells list risk IDs at their current qualitative ratings.

| Impact \ Probability | 1 Rare | 2 Unlikely | 3 Possible | 4 Likely | 5 Almost certain / strongly indicated |
| --- | --- | --- | --- | --- | --- |
| 5 Severe | — | R-07 | R-04, R-05 | R-03 | R-01 |
| 4 Major | — | — | R-06 | R-02 | — |
| 3 Moderate | — | — | R-08 | — | — |
| 2 Minor | — | — | — | — | — |
| 1 Negligible | — | — | — | — | — |

## 4. Top-three risks: mitigation, monitoring, and management (RMMM)

### R-01 — Faculty availability and content shortfall

Risk mitigation: obtain a course-by-course commitment and a rolling recording/handoff calendar; identify a faculty contact and backup for each course; track accepted content, not just scheduled sessions.

Monitoring: weekly planned-versus-actual course recording and acceptance count; escalate any missed handoff immediately.

Management/contingency: Director chooses a staged 8-course launch, a changed scope/date, or formally approved additional capacity. Do not assume faculty can deliver the other 22 courses without evidence.

Owner: Director accountable; faculty leads responsible for content commitments; PM maintains forecast.

### R-03 — Launch expectation and readiness mismatch

Risk mitigation: decide in writing whether “30 at launch” means catalogue entries or 30 complete, learner-ready courses; keep platform-ready and content-ready milestones separate; include content readiness in go/no-go.

Monitoring: show week-10 platform status beside faculty/editor content forecast at every steering review.

Management/contingency: if 30 recorded courses remain mandatory, rebaseline the launch only after a feasible content plan is agreed; otherwise approve staged release.

Owner: Director for scope decision; PM for baseline and reporting.

### R-02 — Editor capacity and rework

Risk mitigation: reserve the supplied 60 editor-hours/week; agree source format, naming, metadata, and quality checks before faculty recording; process batches where possible; capture actual effort per accepted course.

Monitoring: weekly hours consumed, queue size, rejection/rework rate, and forecast finish.

Management/contingency: reprioritise content cohort or reforecast; any added editor capacity requires an approved resource decision, not an assumed plan.

Owner: Editor/content production lead.

## 5. Issue log (events already occurred)

No actual project problems were reported in the supplied case. Do not copy future risks into this table as if they have happened. Open a row only when an event is observed.

| Issue ID | Date raised | Occurred event / impact | Owner | Immediate action | Due date | Status / resolution |
| --- | --- | --- | --- | --- | --- | --- |
| — | None reported as of this planning baseline | No confirmed issues supplied | — | Populate during project execution if an issue occurs | — | Not applicable |

## 6. Closure note and lessons learned

### Current closure status

This note closes the planning exercise only; it does not mean a live CourseCraft project has finished. No deployment, stakeholder workshop, executed test run, confirmed defect log, or actual enrolment results were provided, so none are reported as outcomes.

### What we learned from this planning exercise

Treat content as a first-class dependency. A technically ready platform does not constitute a learner-ready launch when courses lack recordings.

Separate demand ambition from committed capacity. The 30-course goal and 8-course recording capacity must be resolved by a sponsor decision, not hidden in a software schedule.

Show arithmetic and assumptions. The 4.8-week and 18-week figures are editor-capacity calculations; faculty handoff, validation, and rework affect elapsed dates.

Design integrations behind interfaces. Payment and video providers are external dependencies; adapters keep provider change from spreading into course and certificate rules.

Make certificate decisions auditable. Explicit conditions, a decision table, idempotent issuance, and negative tests reduce disputes and accidental awards.

Do not invent quality evidence. DRE and defect density need an executed defect log and code-size baseline; until then, report them as not measurable.

### Before a real handover

Confirm the Director’s launch definition and approved course cohort.

Approve certificate, refund, retake, privacy, accessibility, and retention rules.

Record actual faculty commitments, accepted content dates, editor effort, and release approvals.

Execute the Test Plan, publish real defect metrics, and retain traceable evidence.

Capture actual schedule/cost/scope outcomes and replace anticipated lessons with observed lessons after the release review.